## Pembagian Modul (hidden)
Pembagian Modul Untuk Mapping Table
No | Modul | Table | PIC | Status | Due Date | Endate | Status Table | Name | Status
1 | Common | Tbl_Parameter | Mayer | Closed | 2011-06-24 |  | Closed | Mayer | Open
|  | Tbl_Company |  | Closed | 2011-06-24 |  | Closed | Whidia | In Progress
|  | Tbl_Org_Structure |  | Closed | 2011-06-24 |  | In Progress | Alex Sandro | Closed
|  | Tbl_In_Person |  | Closed | 2011-06-24 |  | Closed | Fitriani | Dropped
|  | Tbl_Ex_Person |  | Closed | 2011-06-24 |  | Closed | Togu | Pending
|  | Tbl_Location |  | Closed | 2011-06-27 | 2011-06-27 | Pending
|  | Tbl_Vehicle_Type |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Vehicle_List |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Driver_Operator |  | Closed | 2011-06-24 |  | Closed
|  | Login |  | Dropped | 2011-06-24 |  | Dropped
|  | Tbl_TypeLocation |  | Closed |  | 2011-06-27 | Pending
2 | Eksplorasi | Tbl_Drilling | Alex Sandro | Closed | 2011-06-24 |  | Closed
|  | Tbl_Drilling_Dtl |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Drilling_Hole_Reconcile |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Geodas_Lithology |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Sample_Analysis |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Parameter_Eksplorasi |  | Closed | 2011-06-24 |  | Closed
3 | Produksi dan view untuk report | Tbl_Dump_Rotation | Whidia | Closed | 2011-06-24 |  | Closed
|  | Tbl_Dump_Rotation_Dtl_Veh |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Dump_Rotation_Dtl_Rot |  | Dropped |  |  | Dropped
|  | Tbl_Dump_Truck_Hauling |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Crusher |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Record_Crusher |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Time_Sheet_Equipment |  | Closed | 2011-06-24 |  | Closed
|  | View |  | Open |  |  | Open
4 | Logistik | Tbl_Part_Group | Fitriani | Closed | 2011-06-24 |  | Closed
|  | Tbl_Storage |  | Closed | 2011-06-27 | 2011-06-27 | Closed
|  | Tbl_Part |  | Closed | 2011-06-27 | 2011-06-27 | Closed
|  | Tbl_Part_Location |  | Closed | 2011-06-24 |  | Pending
|  | Tbl_Daily_Stock |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Part_Request |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Part_Request_Dtl |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Part_Order |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Part_Order_Dtl |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Stock_Opname_Balance |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Fuel_Tanker |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Fuel_Compsution |  | Closed | 2011-06-24 |  | Closed
|  | Tbl_Type_Storage |  | Closed | 2011-06-24 | 2011-06-27 | Pending
5 | Setting environment | Setting Server | Togu | Closed | 2011-06-24 |  | Closed
|  | Kostumisasi Framework SI Del |  | In Progress |  |  | In Progress
|  | Setting User |  | In Progress | 2011-06-27 |  | Closed

## Tabel
Daftar Tabel |  | Total Tabel | Master | 8 |  | Jenis Tabel | Master | Referensi | Transaksi | Header | Detail | Relasi | Total
Data Architect : MAS |  |  | Referensi | 1 |  | Jumlah | 17 | 5 | 14 | 2 | 5 | 5 | 48
DBA : MAS |  |  | Transaksi | 13
|  |  | Header | 2
|  |  | Detail | 1
|  |  | Relasi | q
25
No | Modul | Nama | Jenis | Deskripsi Isi | Status | [6 empty] | Note:
[5 empty] | Designed * |  | Created |  | Modified |  |  | * = Konvensi perubahan nama tabel dan field
[5 empty] | Plan | Real | Plan | Real | Plan | Real
1 | Registrasi | registrasi | Master | Berisi Captcha | 0 | - | 2011-06-20 | 2011-06-20 |  | -
2 | Login | login | Master | This table contains data of companies involved in daily activities (Kutai Energi, vendor, etc) | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
3 | Eksplorasi | eks_m_drilling | Master | This table contains daily drilling | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
|  | eks_d_drilling_dtl | Detail | This table contains daily drilling detail | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
|  | eks_r_parameter_eksplorasi | Referensi | This table contains paremeters used through only exploration module | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
|  | eks_t_drilling_hole_reconcile | Transaksi | This table contains drilling bor open hole reconcile | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
|  | eks_t_geodas_lithology | Transaksi | This table contains data geodas lithology | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
|  | eks_t_sample_analysis | Transaksi | This table contains Analysis of Sample | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
4 | Logistik | log_m_part | Master | This table contains data captured from STOCK PART HARIAN | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
|  | log_m_part_group | Master | This table contains data of various groups/types of part | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
|  | log_m_storage | Master | This table contains data of storage system in warehouse | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
|  | log_h_part_order | Header | This table contains data captured from PART ORDER DEPARTMENT | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
|  | log_h_part_request | Header | This table contains data captured from PART REQUESTION | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
|  | log_t_part_order_dtl | Transaksi | This table contains data captured from PART ORDER DEPARTMENT | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
|  | log_t_part_request_dtl | Transaksi | This table contains data captured from PART REQUESTION | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
|  | log_t_daily_stock | Transaksi | This table contains data captured from STOCK PART HARIAN | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
|  | log_t_fuel_compsution | Transaksi | This table contains data captured from Fuel Consumption Equipment | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
|  | log_t_fuel_tanker | Transaksi | This table contains data fuel in tanker | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
|  | log_t_stock_opname_balance | Transaksi | This table contains data balancing if number of item in system is different from physical count | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
|  | log_x_part_location | Relasi | This table contains data captured from STOCK PART HARIAN=> if item is stored in multiple location | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
5 | Produksi | pro_m_crusher | Master | This table contains data captured from Record Producivity Crusher | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
|  | pro_m_dump_rotation | Master | This table contains data captured from RECORD RITASI DUMP TRUCK | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
|  | pro_t__record_crusher | Transaksi | This table contains data captured from Record Producivity Crusher | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
|  | pro_t_dump_rotation_veh | Transaksi | This table contains data captured from RECORD RITASI DUMP TRUCK=> grouped by vehicle used (DUMP TRUCK or HAUL DUMP) | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12
|  | pro_t_dump_truck_hauling | Transaksi | This table contains data captured from FORMULIR DUMP TRUCK HAULING | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-14
|  | pro_t_time_sheet_equipment | Transaksi | This table contains data captured from Time Sheet Equipment | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 2011-07-12

## Pembagian Form (hidden)
Pembagian Modul Untuk Pembuatan Form dan Validasi
No | Modul | Form | PIC | Validasi | Status | Due Date | Name | Status
1 | Common | Tbl_Parameter | Mayer | Open | Closed |  | Mayer | Open
|  | Tbl_Company |  | Open | Closed |  | Whidia | In Progress
|  | Tbl_Org_Structure |  | Open | Closed |  | Alex Sandro | Closed
|  | Tbl_In_Person |  | Open | Closed |  | Fitriani | Dropped
|  | Tbl_Ex_Person |  | Open | Closed |  | Togu | Pending
|  | Tbl_Location |  | Open | In Progress
|  | Tbl_Vehicle_Type |  | Open | Closed
|  | Tbl_Vehicle_List |  | Open | Closed
|  | Tbl_Driver_Operator |  | Open | Closed
|  | Login |  | Dropped | Dropped
|  | Tbl_TypeLocation |  | Pending | Dropped
2 | Eksplorasi | Tbl_Drilling | Alex Sandro | Open | Closed
|  | Tbl_Drilling_Dtl |  | Open | Closed
|  | Tbl_Drilling_Hole_Reconcile |  | Open | Closed
|  | Tbl_Geodas_Lithology |  | Open | Closed
|  | Tbl_Sample_Analysis |  | Open | Closed
|  | Tbl_Parameter_Eksplorasi |  | Open | Closed
3 | Produksi dan view untuk report | Tbl_Dump_Rotation | Whidia | Open | Closed
|  | Tbl_Dump_Rotation_Dtl_Veh |  | Open | Closed
|  | Tbl_Dump_Rotation_Dtl_Rot |  | Open | Closed
|  | Tbl_Dump_Truck_Hauling |  | Open | Closed
|  | Tbl_Crusher |  | Open | Closed
|  | Tbl_Record_Crusher |  | Open | Closed
|  | Tbl_Time_Sheet_Equipment |  | Open | Closed
|  | View |  | Open | Open
4 | Logistik | Tbl_Part_Group | Fitriani | Open | Closed
|  | Tbl_Storage |  | Open | In Progress
|  | Tbl_Part |  | Open | Closed
|  | Tbl_Part_Location |  | Open | Closed
|  | Tbl_Daily_Stock |  | Open | Closed
|  | Tbl_Part_Request |  | Open | Closed
|  | Tbl_Part_Request_Dtl |  | Open | Closed
|  | Tbl_Part_Order |  | Open | Closed
|  | Tbl_Part_Order_Dtl |  | Open | Closed
|  | Tbl_Stock_Opname_Balance |  | Open | Closed
|  | Tbl_Fuel_Tanker |  | Open | Closed
|  | Tbl_Fuel_Compsution |  | Open | Closed
|  | Tbl_Type_Storage |  | Dropped | Dropped
5 | Setting environment | Setting Server | Togu | Closed | Closed
|  | Kostumisasi Framework SI Del |  | In Progress | In Progress
|  | Setting User |  | Closed | Closed

## Trigger dan View (hidden)
Sampai saat ini belum ada.

## Tabel Detail (hidden)
1. Daftar Tabel Framework SIDEL
No. | Jenis | Nama | Jumlah
1 | Master | sys_m_application | 5
sys_m_imap
sys_m_role
sys_m_table
sys_m_user
2 | Detail | sys_d_function | 3
sys_d_profile
sys_d_unit
3 | Referensi | sys_r_area | 2
sys_r_unit_group
4 | Transaksi | sys_t_access_log | 1
5 | Relasi | sys_x_app_privilege | 4
sys_x_func_privilege
sys_x_unit_privilege
sys_x_user_role
15
2. Daftar Tabel Modul Common
No. | Jenis | Nama | Jumlah
1 | Master | cmn_m_company | 6
cmn_m_ex_person
cmn_m_in_person
cmn_m_location
cmn_m_org_stucture
cmn_m_vehicle_list
2 | Detail | cmn_d_driver_operator | 1
3 | Referensi | cmn_r_parameter | 2
cmn_r_vehicle_type
9
3. Daftar Tabel Modul Eksplorasi
No. | Jenis | Nama | Jumlah
1 | Master | eks_m_drilling | 1
2 | Detail | eks_d_drilling_dtl | 1
3 | Referensi | eks_r_parameter_eksplorasi | 1
4 | Transaksi | eks_t_drilling_hole_reconcile | 3
eks_t_geodas_lithology
eks_t_sample_analysis
6
4. Daftar Tabel Modul Logistik
No. | Jenis | Nama | Jumlah
1 | Master | log_m_part | 3
log_m_part_group
log_m_storage
2 | Header | log_h_part_order | 2
log_h_part_request
3 | Transaksi | log_t_daily_stock | 5
log_t_fuel_compsution
log_t_part_order_dtl
log_t_part_request_dtl
log_t_fuel_tanker
4 | Relasi | log_x_part_location | 1
11
5. Daftar Tabel Modul Produksi
No. | Jenis | Nama | Jumlah
1 | Master | pro_m_crusher | 2
pro_m_dump_rotation
2 | Transaksi | pro_t__record_crusher | 4
pro_t_dump_rotation_veh
pro_t_dump_truck_hauling
pro_t_time_sheet_equipment
6
| Jumlah semua tabel: | 47

## Form
Perkembangan Pembuatan Form
Daftar Form
Form UI Architect : FTN
No. | Nama Modul | Nama Tabel | Kode Form | Nama Form | PIC | Tgl Awal | Tgl Akhir | Status | Name | Status
1 | Registrasi | users | FO-REG-01 | Form Registrasi | Scintya | 2021-04-27 |  | Closed | Donianto | Open
2 | Login | roles | FO-LOG-01 | Form Login | Alex Sandro | 2021-04-27 |  | Closed
|  |  | FO-LOG-02 | Form Lupa Password | Alex Sandro | 2021-04-27 |  | Closed
|  |  | FO-EKS-03 | Form Update Drilling | Alex Sandro | 4-Juli-2011 | 6-Juli-2011 | Closed
|  |  | FO-EKS-04 | Form View Single/All Drilling | Alex Sandro | 4-Juli-2011 |  | In Progress
|  | eks_d_drilling_dtl | FO-EKS-05 | Form Add Drilling Detail | Alex Sandro | 4-Juli-2011 | 6-Juli-2011 | Closed
|  |  | FO-EKS-06 | Form Delete Drilling Detail | Alex Sandro | 4-Juli-2011 | 6-Juli-2011 | Closed
|  |  | FO-EKS-07 | Form Update Drilling Detail | Alex Sandro | 4-Juli-2011 | 6-Juli-2011 | Closed
|  |  | FO-EKS-08 | Form View Single/All Drilling Detail | Alex Sandro | 4-Juli-2011 |  | In Progress
|  | eks_r_parameter_eksplorasi | FO-EKS-09 | Form Add Parameter Eksplorasi | Alex Sandro | 4-Juli-2011 | 6-Juli-2011 | Closed
|  |  | FO-EKS-10 | Form Delete Parameter Eksplorasi | Alex Sandro | 4-Juli-2011 | 6-Juli-2011 | Closed
|  |  | FO-EKS-11 | Form Update Parameter Eksplorasi | Alex Sandro | 4-Juli-2011 | 6-Juli-2011 | Closed
|  |  | FO-EKS-12 | Form View Single/All Parameter Eksplorasi | Alex Sandro | 4-Juli-2011 |  | In Progress
|  | eks_t_drilling_hole_reconcile | FO-EKS-13 | Form Add Drilling Hole Reconsile | Alex Sandro | 4-Juli-2011 | 6-Juli-2011 | Closed
|  |  | FO-EKS-14 | Form Delete Drilling Hole Reconsile | Alex Sandro | 4-Juli-2011 | 6-Juli-2011 | Closed
|  |  | FO-EKS-15 | Form Update Drilling Hole Reconsile | Alex Sandro | 4-Juli-2011 | 6-Juli-2011 | Closed
|  |  | FO-EKS-16 | Form View Single/All Drilling Hole Reconsile | Alex Sandro | 4-Juli-2011 |  | In Progress
|  | eks_t_geodas_lithology | FO-EKS-17 | Form Add Geodas Lithology | Alex Sandro | 4-Juli-2011 | 6-Juli-2011 | Closed
|  |  | FO-EKS-18 | Form Delete Geodas Lithology | Alex Sandro | 4-Juli-2011 | 6-Juli-2011 | Closed
|  |  | FO-EKS-19 | Form Update Geodas Lithology | Alex Sandro | 4-Juli-2011 | 6-Juli-2011 | Closed
|  |  | FO-EKS-20 | Form View Single/All Geodas Lithology | Alex Sandro | 4-Juli-2011 |  | In Progress
|  | eks_t_sample_analysis | FO-EKS-21 | Form Add Sample Analysis | Alex Sandro | 4-Juli-2011 | 6-Juli-2011 | Closed
|  |  | FO-EKS-22 | Form Delete Sample Analysis | Alex Sandro | 4-Juli-2011 | 6-Juli-2011 | Closed
|  |  | FO-EKS-23 | Form Update Part | Alex Sandro | 4-Juli-2011 | 6-Juli-2011 | Closed
|  |  | FO-EKS-24 | Form View Single/All Sample Analysis | Alex Sandro | 4-Juli-2011 |  | In Progress
3 | Logistik | log_m_part | FO-LOG-01 | Form Add Part | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-02 | Form Delete Part | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-03 | Form Update Part | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-04 | Form View Single/All Part | Fitriani | 4-Juli-2011 |  | In Progress
|  | log_m_part_group | FO-LOG-05 | Form Add Part Group | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-06 | Form Delete Part Group | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-07 | Form Update Part Group | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-08 | Form View Single/All Part Group | Fitriani | 4-Juli-2011 |  | In Progress
|  | log_m_storage | FO-LOG-09 | Form Add Storage | Fitriani | 4-Juli-2011 | 14-Juli-2011 | Closed
|  |  | FO-LOG-10 | Form Delete Storage | Fitriani | 4-Juli-2011 | 14-Juli-2011 | Closed
|  |  | FO-LOG-11 | Form Update Storage | Fitriani | 4-Juli-2011 | 14-Juli-2011 | Closed
|  |  | FO-LOG-12 | Form View Single/All Storage | Fitriani | 4-Juli-2011 |  | In Progress
|  | log_m_part_order | FO-LOG-13 | Form Add Part Order | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-14 | Form Delete Part Order | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-15 | Form Update Part Order | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-16 | Form View Single/All Part Order | Fitriani | 4-Juli-2011 |  | In Progress
|  | log_m_part_request | FO-LOG-17 | Form Add Part Request | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-18 | Form Delete Part Request | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-19 | Form Update Part Request | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-20 | Form View Single/All Part Request | Fitriani | 4-Juli-2011 |  | In Progress
|  | log_d_part_order_dtl | FO-LOG-21 | Form Add Part Order Detail | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-22 | Form Delete Part Order Detail | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-23 | Form Update Part Order Detail | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-24 | Form View Single/All Part Order Detail | Fitriani | 4-Juli-2011 |  | In Progress
|  | log_d_part_request_dtl | FO-LOG-25 | Form Add Part Request Detail | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-26 | Form Delete Part Request Detail | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-27 | Form Update Part Request Detail | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-28 | Form View Single/All Part Request Detail | Fitriani | 4-Juli-2011 |  | In Progress
|  | log_t_daily_stock | FO-LOG-29 | Form Add Daily Stock | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-30 | Form Delete Daily Stock | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-31 | Form Update Daily Stock | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-32 | Form View Single/All Daily Stock | Fitriani | 4-Juli-2011 |  | In Progress
|  | log_t_fuel_compsution | FO-LOG-33 | Form Add Fuel Compsution | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-34 | Form Delete Fuel Compsution | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-35 | Form Update Fuel Compsution | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-36 | Form View Single/All Fuel Compsution | Fitriani | 4-Juli-2011 |  | In Progress
|  | log_t_fuel_tanker | FO-LOG-37 | Form Add Fuel Tanker | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-38 | Form Delete Fuel Tanker | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-39 | Form Update Fuel Tanker | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-40 | Form View Single/All Fuel Tanker | Fitriani | 4-Juli-2011 |  | In Progress
|  | log_t_stock_opname_balance | FO-LOG-41 | Form Add Stock Opname Balance | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-42 | Form Delete Stock Opname Balance | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-43 | Form Update Stock Opname Balance | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-44 | Form View Single/All Stock Opname Balance | Fitriani | 4-Juli-2011 |  | In Progress
|  | log_x_part_location | FO-LOG-45 | Form Add Part Location | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-46 | Form Delete Part Location | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-47 | Form Update Part Location | Fitriani | 4-Juli-2011 | 08-Juli-2011 | Closed
|  |  | FO-LOG-48 | Form View Single/All Part Location | Fitriani | 4-Juli-2011 |  | In Progress
4 | Produksi | pro_m_crusher | FO-PRO-01 | Form Add Crusher | Whidia | 4-Juli-2011
|  |  | FO-PRO-02 | Form Delete Crusher | Whidia | 4-Juli-2011
|  |  | FO-PRO-03 | Form Update Crusher | Whidia | 4-Juli-2011
|  |  | FO-PRO-04 | Form View Single/All Crusher | Whidia | 4-Juli-2011
|  | pro_m_dump_rotation | FO-PRO-05 | Form Add Dump Rotation | Whidia | 4-Juli-2011
|  |  | FO-PRO-06 | Form Delete Dump Rotation | Whidia | 4-Juli-2011
|  |  | FO-PRO-07 | Form Update Dump Rotation | Whidia | 4-Juli-2011
|  |  | FO-PRO-08 | Form View Single/All Dump Rotation | Whidia | 4-Juli-2011
|  | pro_t__record_crusher | FO-PRO-09 | Form Add Record Crusher | Whidia | 4-Juli-2011
|  |  | FO-PRO-10 | Form Delete Record Crusher | Whidia | 4-Juli-2011
|  |  | FO-PRO-11 | Form Update Record Crusher | Whidia | 4-Juli-2011
|  |  | FO-PRO-12 | Form View Single/All Record Crusher | Whidia | 4-Juli-2011
|  | pro_t_dump_rotation_veh | FO-PRO-13 | Form Add Dump Rotation Vehicle | Whidia | 4-Juli-2011
|  |  | FO-PRO-14 | Form Delete Dump Rotation Vehicle | Whidia | 4-Juli-2011
|  |  | FO-PRO-15 | Form Update Dump Rotation Vehicle | Whidia | 4-Juli-2011
|  |  | FO-PRO-16 | Form View Single/All Dump Rotation Vehicle | Whidia | 4-Juli-2011
|  | pro_t_dump_truck_hauling | FO-PRO-17 | Form Add Dump Truck Hauling | Whidia | 4-Juli-2011
|  |  | FO-PRO-18 | Form Delete Dump Truck Hauling | Whidia | 4-Juli-2011
|  |  | FO-PRO-19 | Form Update Truck Hauling | Whidia | 4-Juli-2011
|  |  | FO-PRO-20 | Form View Single/All Truck Hauling | Whidia | 4-Juli-2011
|  | pro_t_time_sheet_equipment | FO-PRO-21 | Form Add Time Sheet Equipment | Whidia | 4-Juli-2011
|  |  | FO-PRO-22 | Form Delete Time Sheet Equipment | Whidia | 4-Juli-2011
|  |  | FO-PRO-23 | Form Update Time Sheet Equipment | Whidia | 4-Juli-2011
|  |  | FO-PRO-24 | Form View Single/All Time Sheet Equipment | Whidia | 4-Juli-2011

## Fungsi
Daftar Fungsi dari Proyek SI Kutai Energi
Daftar Fungsi Yang harus direalisasi
Proyek : Sistem Informasi Data Warehousing utk PT. Kutai Energi
Application Name :
1 | Common Application (CMN)
2 | Exploration Application (EKS)
3 | Production Application (PRO)
4 | Logistic Application (LOG)
No. | Code Fungsi | Designed * |  |  |  |  | Coding |  |  |  |  | Tested |  |  |  |  | Accepted
|  | Due Date | End Date | By PIC |  | Status | Due Date | End Date | By PIC |  | Status | Due Date | End Date | By PIC |  | Status | Due Date | End Date | By PIC |  | Status
|  |  |  | Plan | Real |  |  |  | Plan | Real |  |  |  | Plan | Real |  |  |  | Plan | Real
1 | CMN-01 | 2011-06-24 | 2011-07-01 | Mayer | Mayer | Closed | 2011-07-01 | 2011-07-08 | Mayer | Mayer | Closed | 2011-07-25 | 2011-07-28 | Togu | Togu | Closed | [5 empty] | Name | Status
2 | CMN-02 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed | [5 empty] | Mayer | Open
3 | CMN-03 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed | [5 empty] | Whidia | In Progress
4 | CMN-04 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-15 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed | [5 empty] | Alex Sandro | Closed
5 | CMN-05 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-29 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed | [5 empty] | Fitriani | Dropped
6 | CMN-06 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-22 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed | [5 empty] | Togu | Pending
7 | CMN-07 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
8 | CMN-08 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
9 | CMN-09 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
10 | CMN-10 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-15 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
11 | CMN-11 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-29 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
12 | CMN-12 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-22 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
13 | CMN-13 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
14 | CMN-14 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
15 | CMN-15 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
16 | CMN-16 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-15 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
17 | CMN-17 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-29 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
18 | CMN-18 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-22 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
19 | CMN-19 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
20 | CMN-20 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
21 | CMN-21 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
22 | CMN-22 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-15 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
23 | CMN-23 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-29 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
24 | CMN-24 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-22 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
25 | CMN-25 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
26 | CMN-26 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
27 | CMN-27 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
28 | CMN-28 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-15 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
29 | CMN-29 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-29 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
30 | CMN-30 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-22 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
31 | CMN-31 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
32 | CMN-32 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
33 | CMN-33 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
34 | CMN-34 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-15 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
35 | CMN-35 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-29 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
36 | CMN-36 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-22 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
37 | CMN-37 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
38 | CMN-38 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
39 | CMN-39 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
40 | CMN-40 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-15 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
41 | CMN-41 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-29 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
42 | CMN-42 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-22 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
43 | CMN-43 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
44 | CMN-44 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
45 | CMN-45 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
46 | CMN-46 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-15 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
47 | CMN-47 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-29 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
48 | CMN-48 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-22 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
49 | CMN-49 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
50 | CMN-50 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
51 | CMN-51 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-08 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
52 | CMN-52 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-15 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
53 | CMN-53 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-29 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
54 | CMN-54 | 2011-06-24 | 2011-07-01 |  | Mayer | Closed | 2011-07-01 | 2011-07-22 |  | Mayer | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
55 | EKS-01 | 2011-06-24 | 2011-07-01 | Alex Sandro | Alex Sandro | Closed | 2011-07-01 | 2011-07-08 | Alex Sandro | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
56 | EKS-02 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-08 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
57 | EKS-03 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-08 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
58 | EKS-04 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-15 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
59 | EKS-05 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-29 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
60 | EKS-06 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-22 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
61 | EKS-07 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-08 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
62 | EKS-08 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-08 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
63 | EKS-09 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-08 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
64 | EKS-10 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-15 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
65 | EKS-11 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-29 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
66 | EKS-12 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-22 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
67 | EKS-13 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-08 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
68 | EKS-14 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-08 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
69 | EKS-15 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-08 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
70 | EKS-16 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-15 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
71 | EKS-17 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-29 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
72 | EKS-18 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-22 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
73 | EKS-19 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-08 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
74 | EKS-20 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-08 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
75 | EKS-21 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-08 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
76 | EKS-22 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-15 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
77 | EKS-23 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-29 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
78 | EKS-24 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-22 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
79 | EKS-25 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-08 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
80 | EKS-26 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-08 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
81 | EKS-27 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-08 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
82 | EKS-28 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-15 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
83 | EKS-29 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-29 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
84 | EKS-30 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-22 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
85 | EKS-31 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-08 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
86 | EKS-32 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-08 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
87 | EKS-33 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-08 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
88 | EKS-34 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-15 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
89 | EKS-35 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-29 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
90 | EKS-36 | 2011-06-24 | 2011-07-01 |  | Alex Sandro | Closed | 2011-07-01 | 2011-07-22 |  | Alex Sandro | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
91 | LOG-01 | 2011-06-24 | 2011-07-01 | Fitriani | Fitriani | Closed | 2011-07-01 | 2011-07-08 | Fitriani | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
92 | LOG-02 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
93 | LOG-03 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
94 | LOG-04 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-15 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
95 | LOG-05 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-29 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
96 | LOG-06 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-22 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
97 | LOG-07 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
98 | LOG-08 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
99 | LOG-09 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
100 | LOG-10 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-15 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
101 | LOG-11 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-29 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
102 | LOG-12 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-22 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
103 | LOG-13 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
104 | LOG-14 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
105 | LOG-15 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
106 | LOG-16 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-15 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
107 | LOG-17 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-29 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
108 | LOG-18 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-22 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
109 | LOG-19 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
110 | LOG-20 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
111 | LOG-21 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
112 | LOG-22 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-15 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
113 | LOG-23 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-29 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
114 | LOG-24 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-22 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
115 | LOG-25 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
116 | LOG-26 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
117 | LOG-27 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
118 | LOG-28 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-15 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
119 | LOG-29 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-29 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
120 | LOG-30 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-22 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
121 | LOG-31 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
122 | LOG-32 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
123 | LOG-33 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
124 | LOG-34 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-15 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
125 | LOG-35 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-29 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
126 | LOG-36 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-22 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
127 | LOG-37 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
128 | LOG-38 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
129 | LOG-39 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
130 | LOG-40 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-15 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
131 | LOG-41 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-29 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
132 | LOG-42 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-22 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
133 | LOG-43 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
134 | LOG-44 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
135 | LOG-45 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
136 | LOG-46 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-15 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
137 | LOG-47 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-29 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
138 | LOG-48 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-22 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
139 | LOG-49 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
140 | LOG-50 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
141 | LOG-51 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
142 | LOG-52 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-15 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
143 | LOG-53 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-29 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
144 | LOG-54 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-22 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
145 | LOG-55 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
146 | LOG-56 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
147 | LOG-57 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
148 | LOG-58 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-15 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
149 | LOG-59 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-29 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
150 | LOG-60 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-22 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
151 | LOG-61 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
152 | LOG-62 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
153 | LOG-63 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
154 | LOG-64 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-15 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
155 | LOG-65 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-29 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
156 | LOG-66 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-22 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
157 | LOG-67 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
158 | LOG-68 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
159 | LOG-69 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-08 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
160 | LOG-70 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-15 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
161 | LOG-71 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-29 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
162 | LOG-72 | 2011-06-24 | 2011-07-01 |  | Fitriani | Closed | 2011-07-01 | 2011-07-22 |  | Fitriani | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
163 | PRO-01 | 2011-06-24 | 2011-07-01 | Whidia | Whidia | Closed | 2011-07-01 | 2011-07-08 | Whidia | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
164 | PRO-02 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-08 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
165 | PRO-03 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-08 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
166 | PRO-04 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-15 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
167 | PRO-05 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-29 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
168 | PRO-06 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-22 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
169 | PRO-07 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-08 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
170 | PRO-08 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-08 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
171 | PRO-09 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-08 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
172 | PRO-10 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-15 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
173 | PRO-11 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-29 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
174 | PRO-12 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-22 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
175 | PRO-13 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-08 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
176 | PRO-14 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-08 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
177 | PRO-15 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-08 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
178 | PRO-16 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-15 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
179 | PRO-17 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-29 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
180 | PRO-18 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-22 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
181 | PRO-19 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-08 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
182 | PRO-20 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-08 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
183 | PRO-21 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-08 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
184 | PRO-22 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-15 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
185 | PRO-23 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-29 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
186 | PRO-24 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-22 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
187 | PRO-25 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-08 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
188 | PRO-26 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-08 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
189 | PRO-27 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-08 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
190 | PRO-28 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-15 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
191 | PRO-29 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-29 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
192 | PRO-30 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-22 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
193 | PRO-31 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-08 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
194 | PRO-32 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-08 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
195 | PRO-33 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-08 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
196 | PRO-34 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-15 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
197 | PRO-35 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-29 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed
198 | PRO-36 | 2011-06-24 | 2011-07-01 |  | Whidia | Closed | 2011-07-01 | 2011-07-22 |  | Whidia | Closed | 2011-07-25 | 2011-07-28 |  | Togu | Closed

## Tabel-Fungsi
Hasil Mapping Antara Tabel dan Fungsi
No. | Nama Modul | Nama Tabel | Kode Fungsi | Nama Fungsi
1 | Registrasi | users | FU-REG-01 | Registrasi
2 | Login | roles | FU-LOG-01 | Autentikasi Admin
|  |  | FU-LOG-02 | Autentikasi Users
3 | Hasil Tani | hasiltani | FU-HST-01 | Add Data
|  |  | FU-HST-02 | Delete Data
|  |  | FU-HST-03 | Update Data
|  |  | FU-HST-04 | View Data
4 | Produksi | pro_m_crusher | FU-PRO-01 | Add Data
|  |  | FU-PRO-02 | Delete Data
|  |  | FU-PRO-03 | Update Data
|  |  | FU-PRO-04 | Validasi Inputan
|  | pro_m_dump_rotation | FU-PRO-05 | Add Data
|  |  | FU-PRO-06 | Delete Data
|  |  | FU-PRO-07 | Update Data
|  |  | FU-PRO-08 | Validasi Inputan
|  | pro_t__record_crusher | FU-PRO-09 | Add Data
|  |  | FU-PRO-10 | Delete Data
|  |  | FU-PRO-11 | Update Data
|  |  | FU-PRO-12 | Validasi Inputan
|  | pro_t_dump_rotation_veh | FU-PRO-13 | Add Data
|  |  | FU-PRO-14 | Delete Data
|  |  | FU-PRO-15 | Update Data
|  |  | FU-PRO-16 | Validasi Inputan
|  | pro_t_dump_truck_hauling | FU-PRO-17 | Add Data
|  |  | FU-PRO-18 | Delete Data
|  |  | FU-PRO-19 | Update Data
|  |  | FU-PRO-20 | Validasi Inputan
|  | pro_t_time_sheet_equipment | FU-PRO-21 | Add Data
|  |  | FU-PRO-22 | Delete Data
|  |  | FU-PRO-23 | Update Data
|  |  | FU-PRO-24 | Validasi Inputan

## Plan VS Act (hidden)
| Planning |  |  |  |  | Actual
Time | MP | Target | Achieve | Plan Achieve | Total Target | MP | Act. Target | Act. Achieve | Act. Pending | Target
W1 Juni | 4 | 8 | 8 | 8 | 132 | 6 | 18 | 12 | 6 | 132
W2 Juni | 4 | 8 | 16 | 16 | 132 | 5 | 28 | 23 | 5 | 132
W3 Oct | 4 | 8 | 24 | 24 | 132 | 4 | 34 | 31 | 3 | 132
W4 Oct | 4 | 8 | 32 | 32 | 132 | 6 | 45 | 34 | 11 | 132
W3 Nov | 6 | 12 | 44 | 44 | 132 | 8 |  |  |  | 132
W4 Nov | 6 | 12 | 56 | 56 | 132 |  |  |  |  | 132
W1 Dec | 6 | 12 | 68 | 68 | 132 |  |  |  |  | 132
W2 Dec | 6 | 12 | 80 | 80 | 132 |  |  |  |  | 132
W3 Dec | 9 | 16 | 96 | 96 | 132 |  |  |  |  | 132
W4 Dec | 9 | 16 | 112 | 112 | 132 |  |  |  |  | 132
W1 Jan | 9 | 18 | 130 | 130 | 132 |  |  |  |  | 132
W2 Jan | 9 | 18 | 148 | 148 | 132 |  |  |  |  | 132
W3 Jan | 9 | 18 | 166 | 166 | 132 |  |  |  |  | 132
W4 Jan | 9 | 18 | 184 | 184 | 132 |  |  |  |  | 132
W1 Feb | 9 | 16 | 200 | 200 | 132 |  |  |  |  | 132

## Programmer
Period | PIC | Week Target | Week Achieve | Pending | Total Target | Total Achieve | Total Pending
W13 4/19/2021 | Donianto | 9 | 8 | 1 | 9 | 8 | 1 | Mapping Tabel
| Johan | 6 | 6 | 0 | 6 | 6 | 0
| Prayoga | 12 | 11 | 1 | 12 | 11 | 1
Scintya
| Yanti | 6 | 6 | 0 | 6 | 6 | 0
W14 4/26/2021 | Donianto | 9 | 8 | 1 | 9 | 8 | 1 | Revisi dan Normalisasi Tabel
| Johan | 6 | 6 | 0 | 6 | 6 | 0 |  | 36
| Prayoga | 12 | 11 | 1 | 12 | 11 | 1 |  | 24
Scintya
| Yanti | 6 | 6 | 0 | 6 | 6 | 0 |  | 48
W15 3/5/2021 | Donianto | 9 | 8 | 0 | 9 | 9 | 0 | Pembuatan Sql Script | 24
| Johan | 6 | 6 | 0 | 6 | 6 | 0
| Prayoga | 12 | 11 | 0 | 12 | 12 | 0
Scintya
| Yanti | 6 | 6 | 0 | 6 | 6 | 0
W16 8/15/2011 | Mayer | 36 | 0 | 1 | 8 | 7 | 1 | Pembuatan Form
| Alex S | 24 | 1 | 1 | 7 | 6 | 1
| Fitriani | 48 | 1 | 1 | 7 | 5 | 2
| Whidia | 24 | 1 | 1 | 7 | 4 | 3

## Data Entry (hidden)
Daftar Tabel |  | Total Tabel | Master | 17
Data Architect : ??? |  |  | Referensi | 5
DBA : ??? |  |  | Transaksi | 13
|  |  | Header | 2
|  |  | Detail | 5
|  |  | Relasi | 5
47
No | Modul | Nama | Jenis | PIC | Status
[5 empty] | Designed * |  | Created |  | Modified | Jlh. Rec | Pemeriksa | Data Entry
[5 empty] | Plan | Real | Plan | Real | (last) |  |  | Tgl Mulai | Tgl Akhir | Status | Name | Status
1 | Framewok SIDEL (sys) | sys_m_application | Master |  | - | - | 2011-06-20 | 2011-06-20 | - | [5 empty] | Mayer | Open
|  | sys_m_imap | Master |  | - | - | 2011-06-20 | 2011-06-20 | - | [5 empty] | Whidia | In Progress
|  | sys_m_role | Master |  | - | - | 2011-06-20 | 2011-06-20 | 2011-07-04 | [5 empty] | Alex Sandro | Closed
|  | sys_m_table | Master |  | - | - | 2011-06-20 | 2011-06-20 | - | [5 empty] | Fitriani | Dropped
|  | sys_m_user | Master |  | - | - | 2011-06-20 | 2011-06-20 | 2011-07-04 | [5 empty] | Togu | Pending
|  | sys_d_function | Detail |  | - | - | 2011-06-20 | 2011-06-20 | -
|  | sys_d_profile | Detail |  | - | - | 2011-06-20 | 2011-06-20 | -
|  | sys_d_unit | Detail |  | - | - | 2011-06-20 | 2011-06-20 | -
|  | sys_r_area | Referensi |  | - | - | 2011-06-20 | 2011-06-20 | -
|  | sys_r_unit_group | Referensi |  | - | - | 2011-06-20 | 2011-06-20 | -
|  | sys_t_access_log | Transaksi |  | - | - | 2011-06-20 | 2011-06-20 | -
|  | sys_x_app_privilege | Relasi |  | - | - | 2011-06-20 | 2011-06-20 | -
|  | sys_x_func_privilege | Relasi |  | - | - | 2011-06-20 | 2011-06-20 | -
|  | sys_x_unit_privilege | Relasi |  | - | - | 2011-06-20 | 2011-06-20 | -
|  | sys_x_user_role | Relasi |  | - | - | 2011-06-20 | 2011-06-20 | 2011-07-04
1 | Common | cmn_m_company | Master | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  |  |  | 2011-07-15 |  | In Progress | Angripa | Open
|  | cmn_m_ex_person | Master | Tobby | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 126 | Tobby | 2011-07-19 | 2011-07-21 | Closed | Tobby | In Progress
|  | cmn_m_in_person | Master | Tobby | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 120 | Tobby | 2011-07-19 | 2011-07-20 | Closed | Mayer | Closed
|  | cmn_m_location | Master | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 | 2011-07-07 |  |  | 2011-07-15 |  | In Progress | Whidia | Dropped
|  | cmn_m_org_stucture | Master | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 37 | Angripa |  |  |  |  | Pending
|  | cmn_m_vehicle_list | Master | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
|  | cmn_d_driver_operator | Detail | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
|  | cmn_r_parameter | Referensi | Tobby | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 365 | Tobby | 2011-07-15 | 2011-07-21 | Closed
|  | cmn_r_vehicle_type | Referensi | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  |  |  | 2011-07-15 |  | In Progress
2 | Eksplorasi | eks_m_drilling | Master | Tobby | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 287 | Tobby | 2011-07-04 | 2011-07-22 | In Progress
|  | eks_d_drilling_dtl | Detail | Tobby | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 447 | Tobby | 2011-07-08 | 2011-07-22 | In Progress
|  | eks_r_parameter_eksplorasi | Referensi | Tobby | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  |  |  | 2011-07-15 |  | In Progress
|  | eks_t_drilling_hole_reconcile | Transaksi | Tobby | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 | [5 empty] | Open
|  | eks_t_geodas_lithology | Transaksi | Tobby | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 | [5 empty] | Open
|  | eks_t_sample_analysis | Transaksi | Tobby | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 | [5 empty] | Open
3 | Logistik | log_m_part | Master |  | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
|  | log_m_part_group | Master |  | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
|  | log_m_storage | Master |  | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 | 2011-07-07
|  | log_h_part_order | Header |  | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
|  | log_h_part_request | Header |  | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
|  | log_t_part_order_dtl | Transaksi |  | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
|  | log_t_part_request_dtl | Transaksi |  | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
|  | log_t_daily_stock | Transaksi |  | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
|  | log_t_fuel_compsution | Transaksi |  | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
|  | log_t_fuel_tanker | Transaksi |  | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
|  | log_x_part_location | Relasi |  | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28
4 | Produksi | pro_m_crusher | Master | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 | [5 empty] | Closed
|  | pro_m_dump_rotation | Master | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 201 | Angripa | 2011-07-04 | 2011-07-19 | Closed
|  | pro_t__record_crusher | Transaksi | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 | [5 empty] | Closed
|  | pro_t_dump_rotation_veh | Transaksi | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 |  | 600 | Angripa | 2011-07-05 | 2011-07-19 | Closed
|  | pro_t_dump_truck_hauling | Transaksi | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 | [5 empty] | Closed
|  | pro_t_time_sheet_equipment | Transaksi | Angripa | 2011-06-21 | 2011-06-21 | 2011-06-27 | 2011-06-28 | [5 empty] | Closed